## Overview
Field | Value
PS Number | SIH26153
Title | AI based Network Attack Forecasting from Network Traffic Data
Organisation | National Technical Research Organisation (NTRO)
Category / Theme | Software / Blockchain & Cybersecurity
Idea submission deadline | 2026-09-20
Team working cutoff | 2026-09-19
Days left to deadline
Repo | github.com/harishvidyarthcsecs/network-attack-forecasting (private)
Public code link (E1) | TBD — Sujitha
Demo video link (E4) | TBD — Sujitha
Slides link (E5) | TBD — Sujitha
Tracker owner / PM | Kaviya V
Current core completion %
USP 1 | Production-grade MLOps spine (release gate, drift, shadow retrain, honest negatives)
USP 2 | 4 real dataset adapters + published cross-dataset generalisation evidence
USP 3 | End-to-end defender workflow: forecast -> MITRE stage -> attention+SHAP -> STIX-lite alert + SOC PDF

## PS Completion
Metric | Value
Weighted core completion %
Core requirements (R1-R7)
ID | Requirement | Owner | Weight | % done | Weighted | Evidence | Notes
R1 | Feature pipeline: flow CSV + packet/PCAP -> normalised matrix | Jayakumar | 20 | 60 |  | windows.parquet; packet_features.py | packet path trained only on DARPA-98; canonical v2 untrained (D1)
R2 | Trained world model (dynamics, not classifier) + scripts + weights + config | Harish | 25 | 75 |  | lstm_weights.pt; train.py; config.yaml | release_gate.passed=false (D4)
R3 | Supervised dynamics learning; generalises to unseen attacks | Archana | 15 | 45 |  | CTU-13 cross-dataset run | LSTM 0.51 < baseline 0.63 macro-F1 (D3)
R4 | Infiltration engine: K-step sim -> prob timeline + MITRE stage + top features | Archana | 15 | 80 |  | rollout() K=5; mitre.py; attention+SHAP | 4 stages only, no Reconnaissance (D2)
R5 | Explainability per prediction (SHAP or attention), not black-box | Archana | 8 | 90 |  | attention weights + shap.LinearExplainer | SHAP on LogReg proxy (documented)
R6 | Offline demo (Streamlit/Flask/CLI), PCAP or CSV, timeline+flags+stage | Kaviya | 10 | 70 |  | app/app.py; app/api.py; cli.py | PCAP input -> readiness failure (D1)
R7 | Benchmark vs logistic-regression baseline (F1/P/R/FPR) | Harish | 7 | 80 |  | docs/SUBMISSION.md benchmark table | reconcile with failing release gate
Deliverable packaging (E1-E5) — tracked, not in the core rollup
E1 | Source code link (GitHub/Drive) | Sujitha |  | 40 |  | repo private | make public / Drive zip (D5)
E2 | README with setup | Sujitha |  | 95 |  | README.md; README-OPS.md; DEMO_RUNBOOK.md | polish pass
E3 | Architecture doc (max 2 pages) | Archana |  | 85 |  | docs/ARCHITECTURE_NOTE.md | trim to 2 pp; single state story (D6)
E4 | Demo video (max 2 min) | Sujitha |  | 45 |  | docs/DEMO_VIDEO_SCRIPT.md | recording unverified
E5 | Technical presentation (max 5 slides) | Sujitha |  | 55 |  | docs/SLIDES.md | deck unverified

## Team & Work Split
Member | Role | Skills | GitHub | Owns (R# / D#) | Contribution summary
Harish Vidyarth N | Development — model & forecast core | ML / PyTorch; repo admin | harishvidyarth | R2, R7, D4, D5, E1 | dual-head LSTM + K-step rollout; leakage-safe splits + per-class recall + retrain to a passing release gate (D4); LogReg benchmark (R7); CI, branch protection, release tag; make repo public / Drive code link (E1, D5); submit on the portal; mentors Manjari on the attack side
Kaviya V | Development — platform core + PM | AI prototype development; Team Lead | kaviya (branch) | R6, E2 | FastAPI backend + no-build SOC UI; docker compose one-command demo; PCAP/CSV upload; STIX-lite alert + SOC PDF wiring (R6); README + setup instructions (E2); owns Milestones tab + daily-report enforcement
Jayakumar | Prototype — data & packet path | Linux networking | jayakumar-hacker | R1, D1, D2 | CIC-IDS2018 + CTU-13 ingestion, 30s windowing, weak MITRE labels (R1); Scapy/PyShark packet features into a trained fused model (D1); Reconnaissance weak-label rule (D2); wires the end-to-end demo prototype
Archana D | Prototype — explainability & evaluation | AI/DS, Power BI |  | R3, R4, R5, D3, D6, E3 | attention + SHAP per prediction (R5); rolling-horizon eval + K-step engine outputs (R4); cross-dataset generalisation write-up (D3); benchmark visuals; 2-page architecture doc (E3, resolves D6); prototype output panels
Manjari | Pitch + Red-Team (in training) | Reading/writing/analysis; learning offensive testing |  | E5 delivery; feeds D3 | delivers the 5-slide pitch + judge Q&A; being taught to attack — runs nmap / hping3 / replayed-pcap scenarios against the prototype to produce unseen-attack evidence for D3 (mentored by Harish + Jayakumar); see docs/SIH_TEAM_PLAN.md section 6
Sujitha | Media & Design (no git) | Canva, PPT, UI/UX |  | E4 assets, E5 deck | 5-slide deck in Canva (from docs/SLIDES.md); 2-min demo video edit in Canva / CapCut (from docs/DEMO_VIDEO_SCRIPT.md); SOC-UI mockups in Canva/Figma for a dev to implement; diagram polish for the architecture doc. Hands final files to the team — does not touch the repo.

## Milestones
Phase | Window | Goal | Owner | Status | Evidence link
0 | Sep 1 | Tracker sheet live; PS saved; roles locked; commit + push the WIP; tag v0.3-pre-sih | Kaviya / Harish | Not started
1 | Sep 1-6 | D1 packet/PCAP path trained (not gated) + D2 Recon label; D4 release gate green | Jayakumar (D1/D2) / Harish + Kaviya (D4, dev) | Not started
2 | Sep 7-11 | D3 generalisation write-up; final benchmark (R7); 2-page architecture doc (E3, resolves D6); prototype wired end-to-end | Archana / Jayakumar | Not started
3 | Sep 12-15 | 2-min demo video (E4, Sujitha in Canva); 5-slide deck (E5, Sujitha in Canva); docker compose one-command demo on a clean machine; Manjari attack-training run | Sujitha (deck/video) / Kaviya / Manjari | Not started
4 | Sep 16-18 | Buffer + polish; judge Q&A prep; portal submission text (Archana drafts); repo public / Drive link (E1, D5, Harish); pitch dry-run (Manjari) | Harish / Archana / Manjari | Not started
Submit | Sep 19 | Submit on the SIH portal (1-day buffer before 20 Sep) | Harish | Not started

## Daily Reports
Date | Member | Hours | Done today | Blockers | Plan tomorrow | Commit / PR links

## Deviations
ID | Description | Severity | Owner | Fix plan | Status | Resolved date
D1 | PS calls flow AND packet features 'required'; working model is flow-only; PCAP/live path returns a readiness failure | High | Jayakumar | Wire Scapy/PyShark packet features into a trained fused model on DARPA-98 / CICIoT2023; drop the readiness-failure stub from the demo path | Open
D2 | PS wants the full 5-stage MITRE map incl. Reconnaissance; CIC-IDS2018 weak labels never surface a Recon class | Medium | Jayakumar | Add a Recon weak-label rule keyed to port-scan signatures on the flow path; verify a Recon window in the demo | Open
D3 | PS wants generalisation to unseen attacks; CTU-13 cross-dataset test is a loss (LSTM 0.51 < baseline 0.63 macro-F1) | Medium | Archana | Honest domain-shift section: report train-CIC / test-CTU + test-DARPA; add feature-alignment pass; frame remaining gap as scoped future work | Open
D4 | release_gate.passed = false: scenario-id leakage, per-class recall below threshold, one-step macro/micro below threshold | High | Harish | Leakage-safe chronological-per-source splits; per-class validation-window minimums; class-weighted retrain; target a passing gate; keep the failing report as rigor evidence | Open
D5 | Repo hygiene: uncommitted WIP + XDR/response slice unstaged -> reproducibility risk for judges | Medium | Harish | Commit + push the WIP, tag a release, make the repo public (or export a clean Drive zip) before submission | Open
D6 | Two divergent state contracts (78-feat legacy vs 33/79-feat canonical v2); the 2-page doc must tell one story | Low | Archana | Pick the contract that ships, describe only that one in ARCHITECTURE_NOTE.md, move the other to a roadmap line | Open

## Prior Art
Name | Link | Approach | Maturity | What we do better
CyberForecaster (piyushkashyap160-spec) | https://github.com/piyushkashyap160-spec/CyberForecaster | Temporal LSTM world model + Temporal GNN + LogReg baseline; claims F1 0.9826 on CSE-CIC-IDS2018 | Prototype | Their F1 is single-dataset; we publish cross-dataset generalisation + a release gate + drift detection
SIH26153-AI-Network-Attack-Forecasting (SabarishR08) | https://github.com/SabarishR08/SIH26153-AI-Network-Attack-Forecasting | traffic -> anomaly detection -> ML forecasting -> kill chain -> Flask dashboard; reuses NTAV | Working prototype (34 commits) | Forecasting bolted onto a 3rd-party detector; ours is one trained world model with a regression head + dual explainability
AttackForecast (HowSuyash) | https://github.com/HowSuyash/AttackForecast | World model P(S_t+1¦S_t) over 60s CTU-13 states; MITRE rollout; offline CPU | Prototype | We have 4 dataset adapters behind one schema + a fuller platform (FastAPI + Next.js + Streamlit + CLI)
raushankumarsah07 (PS-named repo) | https://github.com/raushankumarsah07/aI-based-network-attack-forecasting-from-network-traffic-data | PyTorch GRU world model, counterfactual what-if rollout, Express/React SOC dashboard, Solidity smart-contract audit trail | Prototype / scaffold | Their blockchain audit trail is real differentiation; our answer is a lighter offline hash-chained prediction log (stretch item)
Threat-Scope (kunalsrivastava8810) | https://github.com/kunalsrivastava8810/Threat-Scope | R Shiny SOC dashboard unifying CVE + malware + intrusion data with ML prediction | Prototype dashboard | Dashboard-first, model-thin; we are model-first with reproducible training config + benchmark
Visual Analytics Tool (cyber-laboratory / verpejas) | https://github.com/cyber-laboratory/Visual_Analytics_Tool | DTW alignment of traffic sequences + RNN-based attack forecasting + visual analytics UI (research, predates SIH) | Research tool / paper artifact | Closest reference architecture; our world-model regression head + MITRE stage mapping go beyond it
KillChainGraph (arXiv 2508.18230) | https://arxiv.org/pdf/2508.18230 | Per-kill-chain-phase classifiers with inter-phase dependencies as a directed graph | Preprint + code | Reference for our stage-mapping design; cite, don't compete
Husak et al. 2015, Computers & Security | https://dl.acm.org/doi/10.1016/j.cose.2015.11.005 | Attack-graph + prediction; canonical network attack forecasting paper | Published, widely cited | Foundational citation
SentinelOne / CyberProof predictive threat intel | https://www.sentinelone.com/cybersecurity-101/threat-intelligence/predictive-threat-intelligence/ | Behavioural-signal correlation + predictive risk scoring (commercial) | Shipping products | They correlate signals; they do not learn a network state-transition model or roll it forward K steps

## Risks
Risk | Impact | Likelihood | Mitigation | Owner
D1 or D4 slips past Sep 6 | High — cascades into every later phase | Medium | Cut the GNN stretch + non-blocking polish first; daily check at standup | Kaviya
Manjari still learning offensive testing at demo time | Medium — weak D3 attack evidence + shaky Q&A | Medium | Structured attack-training plan in docs/SIH_TEAM_PLAN.md section 6; Harish + Jayakumar pair with her twice before Phase 3; canned scenario scripts committed | Harish
Release gate can't be made green in time | High — credibility hit under evaluation | Medium | Ship with the honest failing report + a documented remediation plan rather than hiding it | Harish
Cross-dataset generalisation stays a net loss | Medium — weakens R3 claim | High | Report honestly as domain shift + scoped future work; do not overclaim in the deck | Archana
Demo video / deck started too late | Medium — rushed E4/E5 | Medium | Hard-schedule Phase 3 Sep 12-15; script + slide content already written | Sujitha
Repo stays private at submission | High — E1 fails outright | Low | Phase 4 checklist item with Harish as admin; decision recorded in Milestones tab | Sujitha
Two dozen teams ship the same reference design | Medium — blends in | High | Lead the pitch with the MLOps spine + generalisation evidence, not a bigger single-dataset F1 | Kaviya